## Gantt Chart
IT-353 Project — Gantt Chart
Project Start | 2026-07-19 | Mid-Project Submission | 2026-07-26 | Final Submission | 2026-08-09
Work Method | Sequential | No Project Work | 22–23 July 2026 | Project | IT-353 Project | July 2026 | [12 empty] | August 2026
Task Name | Assigned To | Start | End | Duration | Depends On | 2026-07-19 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-02 | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-07 | 2026-08-08 | 2026-08-09
Requirements Analysis and Project Planning | All Members | 2026-07-19 | 2026-07-19 | 1 | None
Task 1: Gantt Chart | Osama | 2026-07-20 | 2026-07-21 | 2 | Requirements Analysis and Project Planning
No Project Work | All Members | 2026-07-22 | 2026-07-23 | 2 | Task 1: Gantt Chart
Task 2: Low-Fidelity Prototype for 3 Screens | Essa | 2026-07-24 | 2026-07-25 | 2 | No Project Work (Midterm Exams)
Mid-Project Progress Report Submission | All Members | 2026-07-26 | 2026-07-26 | 1 | Task 2: Low-Fidelity Prototype for 3 Screens
Task 3: Context Diagram, Level-0 DFD, and Three Level-1 DFDs | Mansour | 2026-07-27 | 2026-07-29 | 3 | Mid-Project Progress Report Submission
Task 4: Use Case Model and Three Use Case Descriptions | Abduldaem | 2026-07-30 | 2026-07-31 | 2 | Task 3: Context Diagram, Level-0 DFD, and Three Level-1 DFDs
Task 5: Two UML Activity Diagrams | Osama | 2026-08-01 | 2026-08-02 | 2 | Task 4: Use Case Model and Three Use Case Descriptions
Task 6: UML Class Diagram | Abduldaem | 2026-08-03 | 2026-08-04 | 2 | Task 5: Two UML Activity Diagrams
Task 7: Relational Database Design and 3NF | Essa | 2026-08-05 | 2026-08-06 | 2 | Task 6: UML Class Diagram
Final Report Compilation and GitHub Check | All Members | 2026-08-07 | 2026-08-07 | 1 | Task 7: Relational Database Design and 3NF
Final Review and Individual Reflections | All Members | 2026-08-08 | 2026-08-08 | 1 | Final Report Compilation and GitHub Check
Final Project Submission | Osama | 2026-08-09 | 2026-08-09 | 1 | Final Review and Individual Reflections